## template
Alcatel-Lucent Internet CMS
Estimation
v 0.1
2012-03-14

## hypotheses
parameters
duration (month) | 10
operationnal parameters
number of day per months | 20 | for full time equivalent
risk margin | 10% | on global time

## Project - ressources
Entity | Role
| Code | Désignation
CDC ressources, from Cap Gemini China | FACT-PM | Project Manager
| FACT-CSDRU | Drupal Architect
| CGC-TLEAD | Technical Lead
| CGC-SDEV1 | Senior Drupal Developer
| CGC-SDEV1 | Senior Drupal Developer
| CGC-DEV1 | Drupal Developer
| CGC-DEV2 | Drupal Developer
| CGC-TST | Tester
| CGC-SYSADM | System Administrator
| CGC-THMR | Drupal Themer (CSS)
| EXPAT-SDEV | Senior Drupal Developper
| EXPAT-DEV | Drupal Developer
| EXPAT-THMR | Drupal Themer (CSS)
| HSTG-SYSARC | System Architect
| HSTG-CSHOST | Hosting consultant
| HSTG-SYSADM | System Administrator
CDC inner ressources | ALU-PM | Project Manager
| ALU-CDEV | Senior Drupal Developer
| ALU-DEV | Drupal Developer
| ALU-THMR | Drupal Themer (CSS)
A-LU US | HSTG-SYSARC | Project Manager
| HSTG-CSHOST | Global Business Analyst

## Project - ratio
see sheets "project ratio process calculation" for explanation
ratio | 4.3

## Workload - Dev-TU
coefficient |  |  | 4.3
|  |  | Dev U.T | Total effort | Total effort with risk | Mapping in Requiremnet | Mapping in Design | Mapping in <RG Drupal Development Tasks v6> Project Stage | Mapping in <RG Drupal Development Tasks v6> Project Category | Mapping in <RG Drupal Development Tasks v6> Project Task | Mapping in <RG Drupal Development Tasks v6> Project Subtask | CDC Remarks
Launch and startup
Platform(LAMP Drupal GIT) |  |  | 3 | 12.9 | 14.19 |  | 6.1 | G3 to G4 (Build & IST) | 04 - C0133A - Platform Setup | Install and configure Linux | Development
[6 empty] | 4.9 | 5.2.14 | G3 to G4 (Build & IST) | 04 - C0133A - Platform Setup | Install and configure Apache | Development
[6 empty] | 4.9 | 5.2.14 | G3 to G4 (Build & IST) | 04 - C0133A - Platform Setup | Install and configure MySQL | Development
[6 empty] | 4.9 | 5.2.14 | G3 to G4 (Build & IST) | 04 - C0133A - Platform Setup | Install and configure PHP | Development
[6 empty] | 4.9 | 5.2.14 | G3 to G4 (Build & IST) | 04 - C0133A - Platform Setup | Install and configure Drupal | Development
[6 empty] | 4.9 | 5.2.14 | G3 to G4 (Build & IST) | 04 - C0133A - Platform Setup | Integrate applications with version control system | TBD
Set up Drupal architecture (memcache, DB replication, varnish, load balance) in integration server |  |  | 5 | 21.5 | 23.65 | 4.9 | 5.2.14 | G3 to G4 (Build & IST) | 04 - C0133A - Platform Setup | Set up HW platforms | Development
Set up Drupal architecture (LAMP, Eclipse, Druapl, GIT, memcache, DB replication, varnish) in development server |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 04 - C0133A - Platform Setup | Set up HW platforms | Development
total launch |  |  | 13 | 55.9 | 61.49 | [6 empty] | Linux*2+memcache+varnish, Apache*2+load balance, Mysql*2+replication, PHP*2+APC, GIT server*1,Eclipse IDE*n(developer numbers), GIT client*n, network configuration*2, Druapl*n
Inception phase
Project take off, ramp up and KT between team member |  |  | 5 | 21.5 | 23.65 | [6 empty] | It depends on the size of project and number of team members
Design Analysis |  |  | 5 | 21.5 | 23.65 | [6 empty] | May need several rounds clarifications after get the final design
total Inception |  |  | 10 | 43 | 47.3
Content Related Tasks
Create global gateway page |  |  | 5 | 21.5 | 23.65 | 4.12 | 5.2.10
Create static pages / informational pages (5 days per one site) |  |  | 5 | 21.5 | 23.65 | 4.12,4.15 | 5.2.10, 5.2.11 |  |  |  |  | We assume the page number is less than 100
Create contact us page only (1 day per one site) |  |  | 0.5 | 2.15 | 2.365 | 4.12 | 5.2.10, 5.2.11 | G3 to G4 (Build & IST) | 21 - C0133A - Forms | Development of various forms (contact) that may be used throughout the site (but not scoped yet). | TBD
Create menu item (2 days per one site) |  |  | 2 | 8.6 | 9.46 | 4.15.1 | 5.2.11
Content type and entity | [5 empty] | 4.4 | 5.2.1 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure content types and content fields | Product
[6 empty] | 4.4 | 5.2.1 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure content types and content fields | Services
[6 empty] | 4.4 | 5.2.1 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure content types and content fields | Solutions
[6 empty] | 4.4 | 5.2.1 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure content types and content fields | Press Release
[6 empty] | 4.4 | 5.2.1 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure content types and content fields | Article
[6 empty] | 4.4 | 5.2.1 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure content types and content fields | Bios
[6 empty] | 4.4 | 5.2.1 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure content types and content fields | Event
[6 empty] | 4.4 | 5.2.1 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure content types and content fields | Issue
[6 empty] | 4.4 | 5.2.1 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure content types and content fields | Case Study
[6 empty] | 4.4 | 5.2.1 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure content types and content fields | Collateral Asset
[6 empty] | 4.4 | 5.2.1 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure content types and content fields | Video Asset
[6 empty] | 4.4 | 5.2.1 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure content types and content fields | Infographic Asset
Create content types |  |  | 4 | 17.2 | 18.92
Define entity |  |  | 4 | 17.2 | 18.92
Field Grouping |  |  | 4 | 17.2 | 18.92 |  |  | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Field_group (7.x-1.1)
Field settings |  |  | 4 | 17.2 | 18.92
Taxonomy setup(based on 7 vocabulary defined in design document) |  |  | 11 | 47.3 | 52.03 | 4.11 | 5.2.2 | G3 to G4 (Build & IST) | 11 - C0133A - Content Architecture | Configure vocabularies and terms | TBD | Multi-languages is not included, and the estimation is based on 1.5 days/taxonomy
Media management | [5 empty] | 4.15.4 | 5.2.3
Image management |  |  | 5 | 21.5 | 23.65 | [6 empty] | The style and layout of site is totally different, even if image can be migrated from current system, also need effort to customize images based on current design
Video management |  |  | 5 | 21.5 | 23.65 | [6 empty] | Video need to adapt to various widths
File management |  |  | 4 | 17.2 | 18.92
Node management |  |  | 5 | 21.5 | 23.65 | [6 empty] | VBO module configuration
Views Setup | Undo | Undo |  |  |  | 5.2, 5.3 | 5.2.16 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Views (7.x-3.3) | TBD
[6 empty] | 5.2, 5.3 | 5.2.16 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Views Data Export (7.x-3.0-beta5) | TBD
[6 empty] | 5.2, 5.3 | 5.2.16 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Views Datasource (7.x-1.x-dev) | TBD
Setting views | Undo | Undo | 10 | 43 | 47.3
Make views integration(s) | Undo | Undo | 15 | 64.5 | 70.95
Setting up user based dashboard |  |  | 10 | 43 | 47.3
total Content Related Tasks |  |  | 93.5 | 402.05 | 442.255
Frontend Related Tasks (Not include backend UI)
Theming | [5 empty] | 5.2, 5.3, 5.4 | 5.2.16 | G3 to G4 (Build & IST) | 15 - C0133A - Theming | Layout theme with graphics per design specs and page layouts | TBD
[6 empty] | 5.2, 5.3, 5.4 | 5.2.16 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Theme Developer (7.x-1.x-dev)
Theme info definition |  |  | 3 | 12.9 | 14.19
CSS structure definition |  |  | 3 | 12.9 | 14.19
CSS implementation |  |  | 5 | 21.5 | 23.65
CSS optimization |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Performance tuning | CSS and JS aggregation
Templates, preprosessing variables definition |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T1. Homepage
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T2. Industries Landing
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T3. Industries Landing
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T4. Subpage, Three Columns
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T5. Subpage, Two columns
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T6. Article Page
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T7. Product Landing Page
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T8. Product Page
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T9. ATSOI (Campaign) Page
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T10. Search Results
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T11. News Centre Page
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T12. Press Release / Blog Page
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T13. Video Embed Page
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T14. Kira Support Portal
[8 empty] | G3 to G4 (Build & IST) | 14 - C0133A - Country Site Landing Pages | Configure page layouts from wireframes, content types, sitemap, & navigation specs | T15. Country
Setting up variables for use in templates |  |  | 8 | 34.4 | 37.84
Tempaltes files implementation |  |  | 5 | 21.5 | 23.65 | [6 empty] | Will be different if too many views needed
Tempaltes files optimization |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Performance tuning | CSS and JS aggregation
Horizontal Components Implementation | [5 empty] | 5.2, 5.3, 5.4 | 5.2.16
H1. MASTHEAD (Main Navigation + Secondary Navigation + Persona-driven navigation) |  |  | 12 | 51.6 | 56.76 |  |  | G3 to G4 (Build & IST) | 12 - C0133A - Navigation | Configure navigation for primary and secondary links, using sitemap, content types and URL paths | TBD | If we need on-active effect on both main and secondary menu, a lot of coding effort will be neededd
[8 empty] | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | User interface --> Menu block | If we need on-active effect on both main and secondary menu, a lot of coding effort will be neededd
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H1A - Masthead | If we need on-active effect on both main and secondary menu, a lot of coding effort will be neededd
[8 empty] | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H1B - Masthead w Sub Nav | If we need on-active effect on both main and secondary menu, a lot of coding effort will be neededd
H2. FOOTER |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H2 - Footer | A lot of footer menus is there, and also have to embeded My perference/Language option in
H3. DYNAMIC LEADIN |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H3 - Dynamic Leadin | Need to take dynamic JS effect into consideration
H4. HOMEPAGE FEATURES |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H4 - Campaign Features
H5. FIND-IT BAR |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H5 - Find-It-Bar
H6. HP, FOOTER FEATURES |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H6 - HP Footer Features
H7. SUB TITLE/BREADCRUMBS |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H7 - Sub Title / Breadcrumbs
H9. ISSUES MODULE |  |  | 4 | 17.2 | 18.92 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H9 - Issues Module
H10. SOCIAL, DROP-DOWN |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H10 - Social Drop Down | A lot of stuff is unclear, such as "Social Settings"/"My Alcatel-lucent" which may need some additional form creatation. We assume all the settings are saved in cookie,
H11. PREFERENCE, DROP-DOWN |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H11 - Preference, Drop Down | A lot of stuff is unclear, such as "?" besides each dropdown/"Edit my profile".We assume all the settings are saved in cookie.
H12. FIND-IT, DROP-DOWN |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H12 - Find it Drop Down
H13. DIAGRAM |  |  | 0 | 0 | 0 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H13 - Diagram | Assumption: this feature is out of scope
H14. INTERNAL PROMO |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H14 - Internal Promo | If where should the link be embeded, there are three options: link on image/link on text/link on text region, the difficulty of these three options is totally different
H15. DYNAMIC CONTENT VIEWER (5 days/view * 4 views) |  |  | 0 | 0 | 0 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | H15 - Dynamic Content Viewer | Assumption: this feature is out of scope
Center Components Implementation | [5 empty] | 5.2, 5.3, 5.4 | 5.2.16
C1. WELCOME MESSAGE |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C1 - Welcome message
C2. RELATED INFO |  |  | 4 | 17.2 | 18.92 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C2 - Related Info | Need to take dynamic JS effect into consideration
C2A. PAGE FEATURES MODULE (SHORT) |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C2A - Page Features Module (Short)
C2B. PAGE FEATURES MODULE (WIDE) |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C2B - Page Features Module (Wide)
C3A. LARGE FEATURE AND LINKS (SHORT) |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C3A - Lage Feature and Links (Short)
C3B. LARGE FEATURE AND LINKS (WIDE) |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C3B - Lage Feature and Links (Wide)
C4, PAGE FEATURES LIST FORMAT |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C4 - Page Features List Format
C5. BODY COPY |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C5 - Body Copy
C6. RELATED ARTICLES MODULE |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C6 - Related Articles Module
C7, SOCIAL/SHARING TOOLBAR |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C7 - Social Sharing Toolbar | Unknow layout design of "Download documentation", we assume "Share a ticket"/"Sign up for training" is out of scope and "download documentation" just trigger a popup download window.
C8. PRODUCT BENEFITS AND FEATURES |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C8 - Product Benefits and Features
C9. RESULTS LISTING MODULE |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C9 - Results Listing Module
C10. ARTICLE LISTING |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C10 - Article Listing
C11. BROWSE ACCORDION |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C11 - Browse Accordion
C12. BROWSE LISTING |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C12 - Browse Listing
C13. EMBEDDED VIDEO MODULE (WIDE) |  |  | 4 | 17.2 | 18.92 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C13 - Embedded Video Module (Wide) | Unkonw what brightcove can provide, need to take dynamic JS effect into consideration, we assume brightcove provides the video player
C14. DOCUMENTATION FILTER |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | C14 - Documentation Filter | Unknow requirement, we assume this is a filter for the documentation such as PDF
Columns(Right/Left) Components Implementation | [5 empty] | 5.2, 5.3, 5.4 | 5.2.16
R1. HOMEPAGE SOCIAL METER |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | R1 - Homepage Social Meter | Unknow requirement, we assume these number is provided by social medias modules
R2. PAGE INTRO |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | R2 - Page Intro
R3. PAGE STATEMENT |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | R3 - Page Statement
R4. QUOTES |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | R4 - Quotes
R5. NEWSLETTER AND RSS FEEDS |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | R5 - Newsletter and RSS Feeds
R6. PRODUCT IMAGE MODULE |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | R6 - Product Image Module | Need to take dynamic JS effect into consideration. Unknow layout design on zoom in, we assume the plus symbol presents zoon in the picture and no 360 degree effect on product picture
R7. FACTOIDS |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | R7 - Factoids
R8. RELATED PRODUCTS AND SERVICES |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | R8 - Related "Products and Services"
R9. SUBJECT MENU |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | R9 - Subject Menu
R10. MORE VIDEOS SELECTION LIST |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | R10 - More Videos Selection List | Need to take dynamic JS effect into consideration, unknown layout design on click, we assume brightcove can provide this feature
R11. TWITTER FEED LIST |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | R11 - Twitter Feed List
L1. TAKE ACTION |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | L1 - Take Action
L2. 3RD/4TH LEVEL NAVIGATION |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | L2 - 3rd/4th level of navigation
L3. NEWS FEATURE |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | L3 - News Feature
L4. SOCIAL HUB MODULE |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | L4 - Social Hub Module
L5. SEARCH FILTER |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | L5 - Search Filter
L6. RELATED PROMOS |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | L6 - Related Promos
L7. NEWS/BLOG FILTER |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | L7 - News/Blog Filter
L8. SUPPORT PORTAL TABS/SELECTORS |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | L8 - Support Portal Tabs/Selectors
Special Components Implementation | [5 empty] | 5.2, 5.3, 5.4 | 5.2.16
S1. CONTENTLIBRARY DROP-DOWN MENU |  |  | 2 | 8.6 | 9.46 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | S1 - Content Library Drop-Down Menu
S2. SHARE SIDE BAR |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | S2 - Share Side Bar
S2. SHADOW BOX FOR IMAGES/VIDEOS |  |  | 1 | 4.3 | 4.73 |  |  | G3 to G4 (Build & IST) | 13 - C0133A - Internet Landing Pages | Configure views, blocks, panels, & groups | S3 - Shadowbox for images/videos
Mobile Theming | [5 empty] | 4.19
Mobile theme info definition |  |  | 0 | 0 | 0 | [6 empty] | Assumption: mobile site is out of scope
Mobile CSS design |  |  | 0 | 0 | 0 | [6 empty] | Assumption: mobile site is out of scope
Mobile CSS implementation |  |  | 0 | 0 | 0 | [6 empty] | Assumption: mobile site is out of scope
Mobile CSS optimization |  |  | 0 | 0 | 0 | [6 empty] | Assumption: mobile site is out of scope
Mobile tempaltes design |  |  | 0 | 0 | 0 | [6 empty] | Assumption: mobile site is out of scope
Mobile tempaltes files implementation |  |  | 0 | 0 | 0 | [6 empty] | Assumption: mobile site is out of scope
Mobile tempaltes files optimization |  |  | 0 | 0 | 0 | [6 empty] | Assumption: mobile site is out of scope
Mobile Blocks Implementation | [5 empty] | 4.19
Horizontal Components |  |  | 0 | 0 | 0 | [6 empty] | Assumption: mobile site is out of scope
Center Components |  |  | 0 | 0 | 0 | [6 empty] | Assumption: mobile site is out of scope
Special Components |  |  | 0 | 0 | 0 | [6 empty] | Assumption: mobile site is out of scope
Context module configuration |  |  | 7 | 30.1 | 33.11 | [6 empty] | Assumption: this tasks is used for persona, and the estimation is 1 day/persona
Cross browser support | [5 empty] | 4.17
IE 7,8,9 |  |  | 10 | 43 | 47.3 | [6 empty] | 3 browsers supported and a lot of JS embeded
Firefox 4+ |  |  | 5 | 21.5 | 23.65
Safari, Chrome |  |  | 5 | 21.5 | 23.65
Mobile browsers in smartphones |  |  | 0 | 0 | 0 | [6 empty] | Assumption: mobile site is out of scope
Mobile browsers in tablets |  |  | 0 | 0 | 0 | [6 empty] | Assumption: mobile site is out of scope
W3C validator |  |  | 5 | 21.5 | 23.65 | 4.17 |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Performance tuning | CSS and JS aggregation
Accessibility Support |  |  | 0 | 0 | 0 | 4.18 | [5 empty] | Assumption: this feature is out of scope
total Frontend Related Tasks |  |  | 199 | 855.7 | 941.27
Backend Functions Related Tasks
Mobile device detection |  |  | 0 | 0 | 0 | 4.19 | [5 empty] | Assumption: mobile site is out of scope
User customization, profile management and creation | [5 empty] | 4.1, 4.8.2 | 5.2.7, 5.2.4 | G3 to G4 (Build & IST) | 10 - C0133A - User Set Up | Create Drupal roles: admin, editors, contributors, members, etc. | TBD
[6 empty] | 4.1, 4.8.2 | 5.2.7, 5.2.4 | G3 to G4 (Build & IST) | 10 - C0133A - User Set Up | Assign Admin roles | TBD
[6 empty] | 4.1, 4.8.2 | 5.2.7, 5.2.4 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | People --> Account settings
[6 empty] | 4.1, 4.8.2 | 5.2.7, 5.2.4 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | People --> IP address blocking
Custimize user back-ends |  |  | 0 | 0 | 0 | [6 empty] | Assumption: there is no customization on Drupal default backend CMS style and pages
Creating profile template and access control |  |  | 5 | 21.5 | 23.65 | [6 empty] | We assume all roles' profile need customization
Performance achievment (Varnish, Memcache etc) | [5 empty] | 4.9 | 5.2.14 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Development --> Performance
PHP session tuning |  |  | 0 | 0 | 0 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Performance tuning | PHP session tuning
Vanish tunning |  |  | 10 | 43 | 47.3 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Performance tuning | Varnish reverse proxy tuning
Memcache Tunning |  |  | 10 | 43 | 47.3 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Performance tuning | Drupal cache tuning
Database tunning |  |  | 10 | 43 | 47.3
Cache database Tunning and custom modules |  |  | 10 | 43 | 47.3 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Performance tuning | Cache storage tuning
Dual publishing |  |  | 0 | 0 | 0 | Intranet-Drupal Integration_28Feb.doc | 5.2.6 |  |  |  |  | The estimation is based on the first solution in design document. The requirement of second solution is not meationed and current design can not do dual publishing. We assume The estimation is based on the first solution in design document. The requirement of second solution is not meationed and current design can not do dual publishing. We assume the third solution is out of scope
Survery & webform implementation | [5 empty] | 4.3, 4.20 | 5.1.1, 5.2.13
Survery implementation |  |  | 10 | 43 | 47.3 | [6 empty] | Unclear requirement
Webform implementation |  |  | 20 | 86 | 94.6 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Content authoring --> Webform settings | Unclear requirement, assume 10 single or double pages form will be provided
[8 empty] | G3 to G4 (Build & IST) | 21 - C0133A - Forms | Development of various forms (contact) that may be used throughout the site (but not scoped yet). | TBD | Unclear requirement, assume 10 single or double pages form will be provided
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Webform | Unclear requirement, assume 10 single or double pages form will be provided
Workflow and publishing | Historique | Historique | 5 | 21.5 | 23.65 | 4.2 | 5.2.6 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | System --> Actions | We assume only production server publish is considered
[6 empty] | 4.2 | 5.2.6 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Workflow --> Rules | We assume only production server publish is considered
[6 empty] | 4.2 | 5.2.6 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Workflow (7.x-1.0) | We assume only production server publish is considered
[6 empty] | 4.2 | 5.2.6 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Rules (7.x-2.0) | We assume only production server publish is considered
Multi change and version management
Revisioning system |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Revisioning (7.x-1.3)
Changes logging |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Development --> Logging and errors
Drupal Monitoring/Management Processes and Infrastructure |  |  | 5 | 21.5 | 23.65 | 4.9 |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Development --> Logging and errors | site server environment must be monitored, maintained, and managed to support availability, website monitoring, and URL management, it depents on if the Hosting provider has this service, we assume Hosting provider have it.
Sitemap |  |  | 3 | 12.9 | 14.19 | 5.1 |  | G3 to G4 (Build & IST) | 12 - C0133A - Navigation | Configure navigation for primary and secondary links, using sitemap, content types and URL paths | TBD
SEO |  |  | 30 | 129 | 141.9 | 4.7 | 5.2.19 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Search and metadata --> URL aliases | Following features are taken into consideration: IP address change, Site map, SEO Checker, Google and Bing Webmaster Tools, Clean URL, Meta tag, Meta descrption, update/customize 404 page and user-based customization need to be taken into consideration
[6 empty] | 4.7 | 5.2.19 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Search and metadata --> Meta tags | Following features are taken into consideration: IP address change, Site map, SEO Checker, Google and Bing Webmaster Tools, Clean URL, Meta tag, Meta descrption, update/customize 404 page and user-based customization need to be taken into consideration
[6 empty] | 4.7 | 5.2.19 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Search and metadata --> URL redirects | Following features are taken into consideration: IP address change, Site map, SEO Checker, Google and Bing Webmaster Tools, Clean URL, Meta tag, Meta descrption, update/customize 404 page and user-based customization need to be taken into consideration
[6 empty] | 4.7 | 5.2.19 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Search and metadata --> Clean URLs | Following features are taken into consideration: IP address change, Site map, SEO Checker, Google and Bing Webmaster Tools, Clean URL, Meta tag, Meta descrption, update/customize 404 page and user-based customization need to be taken into consideration
[6 empty] | 4.7 | 5.2.19 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Metatag (7.x-1.0-alpha4) | Following features are taken into consideration: IP address change, Site map, SEO Checker, Google and Bing Webmaster Tools, Clean URL, Meta tag, Meta descrption, update/customize 404 page and user-based customization need to be taken into consideration
[6 empty] | 4.7 | 5.2.19 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Pathauto (7.x-1.0) | Following features are taken into consideration: IP address change, Site map, SEO Checker, Google and Bing Webmaster Tools, Clean URL, Meta tag, Meta descrption, update/customize 404 page and user-based customization need to be taken into consideration
[6 empty] | 4.7 | 5.2.19 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Schemaorg (7.x-1.0-beta2) | Following features are taken into consideration: IP address change, Site map, SEO Checker, Google and Bing Webmaster Tools, Clean URL, Meta tag, Meta descrption, update/customize 404 page and user-based customization need to be taken into consideration
[6 empty] | 4.7 | 5.2.19 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | SEO Checklist (7.x-3.0-beta1) | Following features are taken into consideration: IP address change, Site map, SEO Checker, Google and Bing Webmaster Tools, Clean URL, Meta tag, Meta descrption, update/customize 404 page and user-based customization need to be taken into consideration
[6 empty] | 4.7 | 5.2.19 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Redirect (7.x-1.0-beta4) | Following features are taken into consideration: IP address change, Site map, SEO Checker, Google and Bing Webmaster Tools, Clean URL, Meta tag, Meta descrption, update/customize 404 page and user-based customization need to be taken into consideration
DAM (Digital Assets Management) |  |  | 15 | 64.5 | 70.95 | 4.15.4 | 5.2.3 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Media --> File system | Unknown 3rd party integration risk, media filter implementation need to be considered, we assume brightcove provide most of the features for videos
[6 empty] | 4.15.9, 4.15.10 | 5.1.1, 5.2.12, 5.3 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Media --> File types
[6 empty] | 4.15.9, 4.15.10 | 5.1.1, 5.2.12, 5.3 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Media --> Image styles
[6 empty] | 4.15.9, 4.15.10 | 5.1.1, 5.2.12, 5.3 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Media --> Media browser settings
[6 empty] | 4.15.9, 4.15.10 | 5.1.1, 5.2.12, 5.3 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Media --> Image toolkit
[6 empty] | 4.15.9, 4.15.10 | 5.1.1, 5.2.12, 5.3 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | File_entity (7.x-2.0-unstable3)
[6 empty] | 4.15.9, 4.15.10 | 5.1.1, 5.2.12, 5.3 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Media (7.x-1.0-rc3)
[6 empty] | 4.15.9, 4.15.10 | 5.1.1, 5.2.12, 5.3 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Media Browser Plus (7.x-1.0-beta3)
[6 empty] | 4.15.9, 4.15.10 | 5.1.1, 5.2.12, 5.3 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Media translation (7.x-1.0)
Import/Output Content & Feeds implementation | [5 empty] | 4.15.9, 4.15.10 | 5.1.1, 5.2.12, 5.3 |  |  | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Print (7.x-1.0-beta1)
XML content importer |  |  | 5 | 21.5 | 23.65 | [6 empty] | Unclear requirement, we assume the format is well-formed and easy mapping to content type fields
XSLT convertion Excel |  |  | 5 | 21.5 | 23.65 | [6 empty] | Unclear requirement, we assume the format is well-formed and easy mapping to content type fields
XSLT convertion doc |  |  | 5 | 21.5 | 23.65 | [6 empty] | Unclear requirement, we assume the format is well-formed and easy mapping to content type fields
Feeds implementation |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Feeds (7.x-2.0-alpha4)
[8 empty] | G3 to G4 (Build & IST) | 19 -C0133A - Third Party Integration | Integrate third party applications | SimpleFeed
Rating content |  |  | 5 | 21.5 | 23.65 | 4.3 | 5.1.1 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Fivestar (7.x-2.0-alpha1)
[6 empty] | 4.3 | 5.1.1 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Voting API (7.x-2.6)
Comment on content |  |  | 5 | 21.5 | 23.65 | 4.3 | 5.1.1
Permission | [5 empty] | 4.1.10 | 5.1.1 | G3 to G4 (Build & IST) | 10 - C0133A - User Set Up | Configure user roles and permissions | TBD
Node permission |  |  | 5 | 21.5 | 23.65
Field permission |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Field permissions (7.x-1.0-beta2)
Template permission |  |  | 5 | 21.5 | 23.65
Document permission |  |  | 5 | 21.5 | 23.65
Additional Settings | [5 empty] | 4.1.10 | 5.1.1
Site management |  |  | 0 | 0 | 0 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Regional and language --> Regional settings
[6 empty] | 4.9 | 5.2.14 | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | System --> Site information
Cron job settings |  |  | 0 | 0 | 0 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | System --> Cron
Module filter |  |  | 0 | 0 | 0 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | User interface --> Module filter | Configure settings for Module Filter.
Shortcut management |  |  | 0 | 0 | 0 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | User interface --> Shortcuts
RSS publishing |  |  | 0 | 0 | 0 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Web services --> RSS publishing
Installation and Configuration of necessary modules |  |  | 0 | 0 | 0 |  |  | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | CKEditor (7.x-1.6)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Coder (7.x-1.0)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Context (7.x-3.0-beta2)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | CTools (7.x-1.0-rc1)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Date (7.x-2.2)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Devel (7.x-1.3)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Display Suite (7.x-1.5)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Drush (7.x-4.5)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Entity API (7.x-1.0-rc1)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Entity reference (7.x-1.0-beta5)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Filter Permissions (7.x-1.x-dev)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Flag (7.x-2.0-beta6)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | I18n (7.x-1.4)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Masquerade (7.x-1.0-rc4)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Module Filter (7.x-1.6)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Nodequeue (7.x-2.0-beta1)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Panels (7.x-3.0)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Quick Tabs (7.x-3.3)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Robotstxt (7.x-1.0)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | String Overrides (7.x-1.8)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Token (7.x-1.0-rc1)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Variable (7.x-1.1)
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | WYSIWYG (7.x-2.1)
total Backend Functions Related Tasks |  |  | 191 | 821.3 | 903.43
Third Party Integration Related Tasks
Neolane integration |  |  | 5 | 21.5 | 23.65 | 4.2 | 5.1.2, 5.2.12 |  |  |  |  | Unknown 3rd party integration risk, we assume the email server is hosted by Neolane
IDOL search integration | [5 empty] | 4.6 | 5.2.8 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Services (7.x-3.1) | Unknown integration risk with IDOL, we assume IDOL PHP API can be provided, search features is the same as current internet, IDOL expert in ALU can provided necessary support in time.
[6 empty] | 4.6 | 5.2.8 | G3 to G4 (Build & IST) | 19 -C0133A - Third Party Integration | Integrate third party applications | Autonomy Idol | Unknown integration risk with IDOL, we assume IDOL PHP API can be provided, search features is the same as current internet, IDOL expert in ALU can provided necessary support in time.
IDOL custom module for search and indexing |  |  | 20 | 86 | 94.6
Definding what to index |  |  | 5 | 21.5 | 23.65
Crawling and testing |  |  | 10 | 43 | 47.3 | [6 empty] | We assume Crawling will done by IDOL team
Taxonomy management |  |  | 10 | 43 | 47.3
Facet and search pages |  |  | 5 | 21.5 | 23.65
MediaWiki, WordPress |  |  | 5 | 21.5 | 23.65 |  |  | G3 to G4 (Build & IST) | 19 -C0133A - Third Party Integration | Integrate third party applications | MediaWiki | We assume these 3rd application is used by current portal and can be handled by drupal easily
[8 empty] | G3 to G4 (Build & IST) | 19 -C0133A - Third Party Integration | Integrate third party applications | WordPress | We assume these 3rd application is used by current portal and can be handled by drupal easily
Netmining |  |  | 5 | 21.5 | 23.65 | [6 empty] | We assume these 3rd application is used by current portal and can be handled by drupal easily
eBarometer |  |  | 5 | 21.5 | 23.65 | 4.15.4 | 5.1.1 | G3 to G4 (Build & IST) | 19 -C0133A - Third Party Integration | Integrate third party applications | eBaromoter | We assume these 3rd application is used by current portal and can be handled by drupal easily
GL Trade |  |  | 5 | 21.5 | 23.65 | 4.15.4 | 5.1.1 | G3 to G4 (Build & IST) | 19 -C0133A - Third Party Integration | Integrate third party applications | GL Trade | We assume these 3rd application is used by current portal and can be handled by drupal easily
Social Media integration |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | AddThis (7.x-2.1-beta1)
Omniture SiteCatalyst/Google Analytics integration |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 19 -C0133A - Third Party Integration | Integrate third party applications | Omniture SiteCatalyst
Brightcove integration | [5 empty] | 4.15.4 | 5.1.1 | G3 to G4 (Build & IST) | 19 -C0133A - Third Party Integration | Integrate third party applications | Brightcove
Module integration |  |  | 3 | 12.9 | 14.19 |  |  | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Brightcove (7.x-3.2)
Extra themeing as user required |  |  | 5 | 21.5 | 23.65
Akamai Cache |  |  | 10 | 43 | 47.3 |  | 5.2.13 | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Akamai (7.x-1.3) | Unknown 3rd paty integration risk, we assume "Akamai" module can easily handle the required features.
[7 empty] | 5.2.13 | G3 to G4 (Build & IST) | 19 -C0133A - Third Party Integration | Integrate third party applications | Akamai | Unknown 3rd paty integration risk, we assume "Akamai" module can easily handle the required features.
total Third Party Integration Related Tasks |  |  | 99 | 425.7 | 468.27
Migration Related Tasks | [7 empty] | G3 to G4 (Build & IST) | 16 - C0133A - Migration | Migrate content for testing (client may be responsible for bulk content migration) | TBD
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Migrate
[8 empty] | G3 to G4 (Build & IST) | 09 - C0133A - Drupal Module Installation | Install and configure modules | Migrate extras (7.x-2.2)
Static campaign pages (Static) |  |  | 5 | 21.5 | 23.65 | 4.14 | 5.3 |  |  |  |  | We assume the node in drupal can handle the static pages, and the number of static pages is less than 50.
Careers (Taleo) |  |  | 5 | 21.5 | 23.65 | 4.14 | 5.3 | G3 to G4 (Build & IST) | 19 -C0133A - Third Party Integration | Integrate third party applications | Taleo | Unclear requirement, unknown 3rd party integration risk and iframe issue, we assume Taleo can handle all required features, and iframe can well-integrate with career page
News Center (Joomla) |  |  | 20 | 86 | 94.6 | 4.14 | 5.3 |  |  |  |  | Unknown database architecture/page number, we assume the migration can be easily handled by the migrate module, and database structure can be easily mapped with Druapl content type fields
Industry Analysts (Custom) |  |  | 0 | 0 | 0 | 4.14 | 5.3 |  |  |  |  | Assumption: not migrate to Drupal
LTE (Some PHP framework) |  |  | 0 | 0 | 0 | 4.14 | 5.3 |  |  |  |  | Assumption: not migrate to Drupal
ECM migration | [5 empty] | 4.14 | 5.3 |  |  |  |  | Unknown database architecture/page number, we assume the migration can be easily handled by the migrate module, and database structure can be easily mapped with Druapl content type fields
Top-level Menu |  |  | 10 | 43 | 47.3
Products |  |  | 15 | 64.5 | 70.95
Solutions |  |  | 15 | 64.5 | 70.95
IP Support |  |  | 10 | 43 | 47.3
Events |  |  | 10 | 43 | 47.3
total Migration Related Tasks |  |  | 90 | 387 | 425.7
Testing Related Tasks | [11 empty] | Since ratio take testing into consideration, we list zero effort here, but following tasks covers all kinds of test we will do.
Unit testcase |  |  | 0 | 0 | 0 |  | 6.4.1 | G2 to G3 (Design) | 06 - C0133A - Testing Process Development | Document testing strategies | Unit testing | We consider it is highly important that unit tests should be written and fully executed for all the core modules/functionalities(60 autobox modules and 40 core modules, we assume 5days/module at least)
IST testcase |  |  | 0 | 0 | 0 |  | 6.4.2 | G2 to G3 (Design) | 06 - C0133A - Testing Process Development | Document testing strategies | Functional testing | Assume this is for Intergation System Functional Testing only, NOT including any other types testing, likely: OS & Browser Combination Testing, Performance/Stress Testing, Security Testing, Language Testing, Mobile Testing, etc The testing will use English version as basic firstly and then verify the key Web pages in French version.
[7 empty] | 6.4.2 | G2 to G3 (Design) | 06 - C0133A - Testing Process Development | Document testing strategies | Integration testing | Assume this is for Intergation System Functional Testing only, NOT including any other types testing, likely: OS & Browser Combination Testing, Performance/Stress Testing, Security Testing, Language Testing, Mobile Testing, etc The testing will use English version as basic firstly and then verify the key Web pages in French version.
Automated Acceptance Testing |  |  | 0 | 0 | 0 |  | 6.4.3
UAT testcase review |  |  | 0 | 0 | 0
Unit testing |  |  | 0 | 0 | 0 |  |  | G2 to G3 (Design) | 06 - C0133A - Testing Process Development | Document testing strategies | Unit testing
IST testing |  |  | 0 | 0 | 0 |  | 6.4.2 | G2 to G3 (Design) | 06 - C0133A - Testing Process Development | Document testing strategies | Functional testing | Assume this is for Intergation System Functional Testing only, NOT including any other types testing, likely: OS & Browser Combination Testing, Performance/Stress Testing, Security Testing, Language Testing, Mobile Testing, etc The testing will use English version as basic firstly and then verify the key Web pages in French version.
[7 empty] | 6.4.2 | G2 to G3 (Design) | 06 - C0133A - Testing Process Development | Document testing strategies | Integration testing | Assume this is for Intergation System Functional Testing only, NOT including any other types testing, likely: OS & Browser Combination Testing, Performance/Stress Testing, Security Testing, Language Testing, Mobile Testing, etc The testing will use English version as basic firstly and then verify the key Web pages in French version.
Performance testing |  |  | 0 | 0 | 0 |  |  | G2 to G3 (Design) | 06 - C0133A - Testing Process Development | Document testing strategies | Performance testing | Assume 5% core functions only need to have Performance Testing
Security testing |  |  | 0 | 0 | 0 |  |  | G2 to G3 (Design) | 06 - C0133A - Testing Process Development | Document testing strategies | Security testing | Assume perform the basic Security tesitng for the critical functions only
Cross browser testing |  |  | 0 | 0 | 0 | [6 empty] | Assume need test on top 5 Browsers except the basic one on IST testing, we select 10%-20% core functions of IST testing to do
Other testing work |  |  | 0 | 0 | 0 |  |  | Approval & Readiness (G4 to G5) | 22 - C0133A - Testing | Verify functional requirements are met | TBD | TBD
[8 empty] | Approval & Readiness (G4 to G5) | 22 - C0133A - Testing | Verify design requirements are met (UI/UX: User interface/User experience) | TBD | TBD
[8 empty] | Approval & Readiness (G4 to G5) | 22 - C0133A - Testing | Verify services work as expected | TBD | TBD
[8 empty] | Approval & Readiness (G4 to G5) | 22 - C0133A - Testing | Verify admin functions work as expected | TBD | TBD
[8 empty] | Approval & Readiness (G4 to G5) | 22 - C0133A - Testing | Verify security measures provide protection | TBD | TBD
total Testing Related Tasks |  |  | 0 | 0 | 0
Documentation Related Tasks
Implementation Plan |  |  | 0 | 0 | 0 | 5 | G2 to G3 (Design) | G2 to G3 (Design) | 02 - C0133A - Design | Create physical design | Finalize system specs (Identify website platforms and software for development and deployment) | Many Requirement is TBD now, since the desgin document is a high level design, we need to do a lot of research on different category such as search and mobile device
[6 empty] | 5 | G2 to G3 (Design) | G2 to G3 (Design) | 02 - C0133A - Design | Create physical design | Finalize content migration instructions (who and how)
[6 empty] | 5 | G2 to G3 (Design) | G2 to G3 (Design) | 02 - C0133A - Design | Create physical design | Finalize deployment instructions for construction, testing, and production
[6 empty] | 5 | G2 to G3 (Design) | G2 to G3 (Design) | 02 - C0133A - Design | Create physical design | Finalize performance and capacity specs
[6 empty] | 5 | G2 to G3 (Design) | G2 to G3 (Design) | 02 - C0133A - Design | Create physical design | Finalize security specifications for configuring website and server
[6 empty] | 5 | G2 to G3 (Design) | G2 to G3 (Design) | 02 - C0133A - Design | Create physical design | Finalize site actions/process workflow specs for performing related user functions
[6 empty] | 5 | G2 to G3 (Design) | G2 to G3 (Design) | 01 - C0133A - I&G Deliverables | Complete physical design | TBD
Database Dictionary |  |  | 0 | 0 | 0
Developers Guide |  |  | 0 | 0 | 0
User Guide |  |  | 0 | 0 | 0 |  |  | G3 to G4 (Build & IST) | 07 - C0133A - Operation Process Development | Document operation processes | Tasks for roles and functions
[8 empty] | G3 to G4 (Build & IST) | 07 - C0133A - Operation Process Development | Document operation processes | Content workflow
Environment Configuration Guide |  |  | 0 | 0 | 0
Deployment Plan |  |  | 0 | 0 | 0 |  |  | G2 to G3 (Design) | 07 - C0133A - Operation Process Development | Document operation processes | Deployment processes
Outage |  |  | 0 | 0 | 0
Release notes |  |  | 0 | 0 | 0
total Documentation Related Tasks |  |  | 0 | 0 | 0
TOTAL With One Site |  |  | 695.5 | 2990.65 | 3289.715
TOTAL With One Site and 2 languages(English France) |  |  | 702.455 | 3020.5565 | 3322.6122 |  |  | G3 to G4 (Build & IST) | 08 - C0133A - Drupal Configuration | Configure additional settings in Drupal | Regional and language --> Regional settings
|  |  |  | full time | 16.4486